## Cover
LifeOS Support Tickets
10 tiket simulasi + 2 insiden nyata (T-001, T-002)

## Tickets
ID | Judul | Severity | Status | Opened | Closed | Timeline | Diagnosis | Resolusi | Pencegahan
T-001 | Login gagal massal (CORS origin :5173 vs :5174) | High | Closed | 2026-09-14 | 2026-09-14 | 1. Lapor: tak bisa login 2. Log hanya OPTIONS tanpa POST 3. Temu: FRONTEND_URL default :5173 4. Fix: restart FRONTEND_URL=:5174 5. Verifikasi: ACAO benar + login 200 | CORS origin mismatch (matrix | Restart API dengan FRONTEND_URL benar + koreksi .env.example | Checklist runbook
T-002 | Database tak sengaja terhapus (simulasi) | High | Closed | 2026-09-14 | 2026-09-14 | 1. Simulasi: rm lifeos.db di /tmp 2. Backup harian tersedia 3. Restore via skrip 4. Verifikasi: 25 tasks + 19 goals kembali | Human error (simulasi terkontrol) | Roundtrip backup→hapus→restore OK | Backup otomatis harian + guard restore tolak saat API jalan
T-003 | 401 semua user setelah ganti secret | Medium | Closed | 2026-09-13 | 2026-09-13 | 1. Lapor: semua sesi logout 2. Cek: JWT_SECRET baru di-deploy 3. Konfirmasi by design | Token lama tak valid dengan secret baru (matrix | Komunikasi ke user: login ulang | Umumkan rotasi secret sebelum deploy
T-004 | Seed error UNIQUE (users) | Low | Closed | 2026-09-12 | 2026-09-12 | 1. Seed dijalankan 2x 2. Cek COUNT users = 1 3. Skip seed (data sudah ada) | Seed tak idempoten (matrix | Tak perlu aksi; dokumentasikan reset bila perlu | Cek COUNT sebelum seed
T-005 | Dashboard lambat saat tasks menumpuk | Low | Open | 2026-09-14 |  | 1. Observasi: N+1 (tasks + habits per item) | Query agregat per baris, belum dioptimasi |  | Indeks + agregat SQL bila tasks > 1000
T-006 | Web blank setelah update | Medium | Closed | 2026-09-11 | 2026-09-11 | 1. Lapor: putih 2. curl title OK 3. Ternyata cache browser lama | Cache (matrix | Hard refresh; verifikasi build hijau | Versioned asset (Vite hashing sudah)
T-007 | Backup 0 byte | Medium | Closed | 2026-09-10 | 2026-09-10 | 1. Cek ukuran backup 2. df: partisi penuh (simulasi) 3. Bersihkan + rerun | Disk penuh (matrix | Rotasi 7 hari + monitor df | Alert saat avail < 10%
T-008 | Token expired tengah sesi | Low | Closed | 2026-09-09 | 2026-09-09 | 1. Auto-logout setelah 24 jam 2. Login ulang OK | exp JWT 24 jam (by design, matrix | Login ulang | Dokumentasikan di FAQ
T-009 | Migrasi pending setelah pull | Low | Closed | 2026-09-08 | 2026-09-08 | 1. Endpoint baru 404 2. goose status: 2 Pending 3. goose up OK | Lupa migrate (matrix | goose up + restart | Checklist deploy: migrate dulu
T-010 | Salah sangka PUT hapus field | Low | Closed | 2026-09-07 | 2026-09-07 | 1. Lapor: data hilang 2. Cek: PUT full-replace by design 3. UI kirim penuh OK | Ekspektasi vs kontrak (BUG-001 QA) | Edukasi + README menegaskan | Kontrak PUT didokumentasikan di swagger

## SLA
SLA compliance (COUNTIF hidup)
Metrik | Nilai
Total tiket | 10
Closed
Open
High severity
Closed rate